## Front Cover
Hornsea Project Four:
Preliminary Environmental Information Report (PEIR)
Volume 4, Annex 5.2:
Commitment Register
Prepared | Rachel Hall & Anisha Lakhani, Ørsted, 23 July 2019
Checked | Anisha Lakhani, Ørsted, 23 July 2019
Accepted | Thomas Watts, Ørsted, 23 July 2019
Approved | Julian Carolan, Ørsted, 23 July 2019

## Contents
1 | Glossary: | Presents defined terms and acronyms used within the Commitments Register.
2 | Relevant Documents: | Provides a list of the relevant additonal documents, for example outline plans and management strategies.
3 | Overview - Commitments Register Explained: | Provides an overview of the Commitments Register and how to use it.
4 | Commitments Register: | A Register of all Hornsea Four Commitments and details of how Commitments are secured.
5 | RPSS & Scoping Change Log: | A change log which illustrates any changes made to the RPSS & Scoping Commitments and an explantion for
such changes.
6 | Public Commitments: | A log of all Commitments suggested by members of the public at Local Information Events and relevant
cross referencing to the Register.

## 1.Glossary
1. Glossary |  |  | Acronyms
| Term | Definition | Acronym | Definition
| Annex 1 habitats | A type of habitat listed in Annex I of Council Directive 92/43/EEC on the conservation of natural habitats and of wild fauna and flora. | AEZs | Archaeological exclusion zones
| Connection works | Work Nos. 6 to 10 of the draft DCO and any related further associated development in connection with those works. | CAA | Civil Aviation Authority
| Joint bays | An excavation located at regular intervals along the cable route consisting of a concrete flat base slab constructed beneath the ground to facilitate the jointing together of the cables. | CoCP | Code of Construction Practice
| Link boxes | These are smaller pits, compared to JBs, which house connections between the cable shielding, joints for fibre optic cables and other auxiliary equipment. | DCO | Development Consent Order
| Logistics compounds | A construction site associated with the connection works including central offices, welfare facilities, and storage for construction of the works. | DML | Deemed Marine License
| Maintenance period | To inspect, upkeep, repair, adjust, and alter and further includes remove, reconstruct and replace, to the extent assessed in the environmental statement. | ECoW | Ecological Clark of Works
| Mitigation | A term used interchangeably with Commitment(s) by Hornsea Four. Mitigation measures (Commitments) are embedded within the assessment at the relevant point in the EIA (e.g. at Scoping or PEIR). | ERCoP | Emergency Response and Cooperation Plan
| Mobilisation period | Arrival and departure of the workforce, site inspections, safety checks, site meetings, low-key maintenance and safety checking. A full description is provided in the outline CoCP. | HDD | Horizontal Directional Drill
| Primary Commitment | Measures that form an intrinsic part of the design that are described in the design evolution narrative and included within the project description e.g. reducing development heights to reduce visual impact. | HGV | Heavy Goods Vehicle
|  |  | IDB | Internal Drainage Board
| Relevant Planning Authority | East Riding of Yorkshire Council, or any successor to it as planning authority for the land in question. | LIE | Local Information Event
| Regular Operator | Commercial operator whose vessel(s) are observed to transit through a particular region on a regular basis. | LLFA | Lead local flood authority
| Secondary Commitment | Measures that require further activity in order to achieve the anticipated outcome, e.g. development of the optimal reinstatement measures for restoring a disturbed sensitive natural habitat. | MCA | Marine Conservation Zone
| Tertiary Commitment | Imeasures which will be required regardless of the EIA process as they are imposed e.g. as a result of legislative requirements and/or standard industry practices e.g. via a Construction Environmental Management Plan (CEMP), Code of Construction Practice (CoCP) or similar. | MCZ | Marine Conservation Zone
|  |  | MHCC | Marine Helicopter Coordination Centre
|  |  | MHWS | Mean High Water Springs
|  |  | MMO | Marine Management Organisation
|  |  | MSL | Mean Sea Level
|  |  | NSR | Nearest Sensitive Receptor
|  |  | PEIR | Preliminary Environmental Information Report
|  |  | PRA | Preliminary Risk Assessment
|  |  | ProW | Public Rights of Way
|  |  | RPSS | Route Planning and Site Selection
|  |  | SAC | Special Area of Conservation
|  |  | SPA | Special Protection Area
|  |  | SSSI | Site of Special Scientific Interest
|  |  | WSI | Written Scheme of Investigation

## 2.Relevant Documents
2. Relevant Documents
| Document Name | Document Reference | DCO Reference
| Draft Development Consent Order (DCO) | C1.1 | n/a
| DCO Works Plans - Offshore (Draft) | D1.1.2 | n/a
| DCO Works Plans - Onshore (Draft) | D1.1.3 | n/a
| Outline Code of Construction Practice (CoCP) | F2.2 | DCO Requirement 16
| Outline Design Vision Statement | A4.4.6 | n/a
| Outline Onshore Infrastructure Drainage Strategy | F2.6 | DCO Requirement 12
| Outline Ecological Management Plan (EMP) | F2.3 | DCO Requirement 9
| Outline Marine Written Scheme of Investigation (WSI) | F2.4 | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 14(2)
| Outline Marine Mammal Mitigation Protocol (MMMP) | F2.5 | DCO Schedule 11, Part 2 - Condition 12(1)(g) and; DCO Schedule 12, Part 2 - Condition 14(1)(g)

## 3.Overview
3. Overview
Hornsea Four has adopted a number of Primary, Secondary and Tertiary Commitments (see glossary for definitions) as part of the EIA process in order to avoid or reduce impacts where possible. This annex details all Commitments that are taken forward within the PEIR and provides details as to how the Commitments are secured, for example by providing cross referencing to the DCO and relevant management plans. A full list of documents which are relevant to and should be read in conjunction with the Commitments Register is set out in Section 2. Commitments have been informed through consultation on the Scoping Report, subsequent informal consultation with a range of key consultees and feedback from members of the public at Local Information Events. An overview of the consultation undertaken to date is provided within Volume 1, Chapter 6: Consultation. Following formal consultation on the PEIR, the Commitments Register will be updated to include new or amended Commitments in response to feedback where possible. The following tables provides an overview of the information contained within the Commitment Register.
Table 1: Commitment Register (Section 4) Explained |  | Table 2: RPSS & Scoping Change Log (Section 5) Explained
Commitment Reference | Each Commitment has a unique ID assigned to it to enable consultees to easily track the evolution of commitments throughout the development of the project. | Commitment Reference | Each Commitment has a unique ID assigned to it to enable consultees to easily track the evolution of commitments throughout the development of the project.
Commitment Stage | Relates to the stage of the project when the Commitment was made (i.e, RPSS, Scoping, LIE, PEIR).
Type | Details whether the Commitment is Primary, Secondary or Tertiary (see Glossary for definitions). | Commitment Stage | Relates to the stage of the project when the Commitment was made.
Hornsea Four Commitment | Details the Commitment made by Hornsea Four. | Hornsea Four Commitment | Details the Commitments made by Hornsea Four at RPSS and Scoping stages of the project which have since been revised or removed. Text which is strike through has been removed from the Commitment and is no longer included within the Commitment Register. Text in red is new text which has now been added to the Commitments within the Commitment Register.
Project Phase | Details the project phase the commitment is relevant to (e.g. construction).
Project Element | Details the project elements the commitment is relevant to (e.g. Co96 which is relevant to agreement on the layout of the turbines would be relevant to the 'array').
Onshore Topic relevance | Details the onshore topics which the Commitment is relevant to. The user can filter by topic to allow all Commitments relevant to a specific topic to be seen. The Commitment will also be detailed within the identified Onshore Chapters of the PEIR. | Explanation of the change | Provides an explanation for the changes made to RPSS and Scoping Commitments. For example commitments may have been updated to provide clarity or where possible remove ambiguous statements. Commitments may also have been merged to streamline the commitments which are proposed by the project.
Offshore Topic relevance | Details the offshore topics which the Commitment is relevant to. The user can filter by topic to allow all Commitments relevant to a specific topic to be seen. The Commitment will also be detailed within the identified Offshore Chapters of the PEIR.
How is the Commitment secured? | Details the mechanism for how the Commitment is to be legally secured (for example through inclusion of a Requirement of the DCO). | Table 3: Public Commitments (Section 6) Explained
When (e.g. pre-construction) | Where Commitments are secured though a management Strategy or Plan (for example the Code of Construction Practice) this column provides details in relation to the timing for final approval of the Strategy or Plan. | Public Commitment Reference | Members of the public were asked to provide suggested Commitments during the Local Information Events. Each suggestion was given a unique reference number.
Who (decision maker) | Where Commitments are secured though a management Strategy or Plan (for example the Code of Construction Practice) this column provides details in relation to the decision maker for final approval of the Strategy or Plan. | Public Commitment/ Comment | Details the Commitment or comment made by the member of the public.
Relevant Application Documents (at PEIR stage) | Where Commitments are secured though a management Strategy or Plan, Hornsea Four has sought to provide an Outline of that Strategy or Plan at PEIR for early consultation. Where this is the case this is detailed within this column. An overview of the Strategies and Plans provided at PEIR stage can be found in Section 2 of this Register. Hornsea Four will seek to provide further outline plans and updated drafts at DCO Application. | Hornsea Four Action | Details how the comment was responded to: i.e. New commitment made; an existing commitment was amended to accommodate the comment made; the comment is covered by an existing comment; or the comment is noted and requires no further action.
|  | Relevant Commitment Reference | Provides a reference to the new or relevant updated/existing commitments which are included within the Commitment Register (Section 4).
|  | Hornsea Four Response | Hornsea Fours response to the comment made and an explanation as how this has been taken into consideration within the Commitment Register.

## 4.Commitments Register
Scoping Opinion PINS Response
4. Commitment Register
The caveat on this doesn't provide confidence
[5 empty] | Project Element |  |  |  |  | Onshore Topic relevance | [8 empty] | Offshore Topic relevance | [13 empty] | Must include further Geo SSSI sites (see PINS ID 4.13.2)
Commitment Reference | Commitment Stage | Type | Hornsea Four Commitment | Project Phase | Onshore ECC | Offshore ECC | Landfall | Onshore Substation (ONSS) | Array | Geology & Ground Conditions | Hydrology & Flood Risk | Historic Environment | Land Use & Recreation | Landscape & Visual | Noise & Vibration | Ecology | Air Quality | Traffic & Transport | Marine Processes | Benthic & Intertidal Ecology | Fish & Shellfish | Marine Mammals | Offshore & Intertidal Ornithology | Commercial Fisheries | Shipping & Navigation | Aviation and Radar | Marine Archaeology | Infrastructure & Other Users | How is the Commitment secured? | When (e.g. pre-construction) | Who (decision maker) | Relevant Application Documents (at PEIR stage)
Co1 | Scoping | Primary | All main rivers, Internal Drainage Board (IDB) maintained drains, main roads and railways will be crossed by HDD or other trenchless technology as set out in the Onshore Crossing Schedule. Where HDD technologies are not practical, the crossing of ordinary watercourses may be undertaken by open cut methods. In such cases, temporary measures will be employed to maintain flow of water along the watercourse. | Construction | X |  | X | X |  | X | X |  |  | X |  | X |  | X | [10 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co2 | RPSS | Primary | The following sensitive sites will be avoided by the permanent project footprint: Listed Buildings (580 sites), Registered Parks and Gardens (Thwaite Hall and Risby Hall), Scheduled Monuments (30 sites), Conservation Areas (19 sites), non-designated built heritage assets (368 sites) and Ancient Woodland (10 sites and TPOs). Please refer to PEIR Volume 6, Annex 6.5.1 Appendix B Designated Assets Gazetteer for detailed lists of designated heritage assets that are avoided by Hornsea Four. With the exception of River Hull Headwaters SSSI, sensitive sites have been avoided. Please refer to PEIR Volume 6, Annex 3.1: Extended Phase 1 Habitat Survey Report for details. Where possible, unprotected areas of woodland, mature, and protected trees (e.g. veteran trees) shall also be avoided or micro sited around. | Construction | X |  | X | X |  | X |  | X |  | X |  | X | [12 empty] | DCO Works Plan - Onshore | n/a | n/a | DCO Works Plan - Onshore (Doc No. D1.4.2)
Co4 | PEIR | Tertiary | A Pollution Prevention Plan (PPP) will be developed in accordance with the outline PPP and will include details of emergency spill procedures. Good practice guidance detailed in the Environment Agency’s Pollution Prevention Guidance (PPG) notes (including PPG01, PPG05, PPG08 and PPG21) will be followed where appropriate, or the latest relevant available guidance. | Construction | X |  | X | X |  | X | X |  |  |  |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co6 | PEIR | Tertiary | During construction of piled foundations, the following guidance will be used: Piling and Penetrative Ground Improvement Methods on land Affected by Contamination: Guidance on Pollution Prevention (Environment Agency, 2001), or latest relevant available guidance. | Construction |  |  |  | X |  | X | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co7 | Scoping | Primary | The temporary work area associated with onshore export cable corridor will be 80m working width to minimise the construction footprint, except the Network Rail Crossing near Beswick where the footprint is extended to 120m to facilitate HDD of the railway line. The permanent onshore export cable corridor width will be 60m except the Network Rail Crossing near Beswick where the footprint is extended to 120m to facilitate HDD of the railway line. | Construction | X |  |  |  |  | X | X | X | X | X | [14 empty] | DCO Works Plan - Onshore | n/a | n/a | DCO Works Plan - Onshore (Doc No. D1.4.2)
Co8 | PEIR | Tertiary | Stockpiles will be a maximum of 2 m high to avoid compaction from the weight, in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298 or the latest relevant available guidance. | Decommissioning | X |  | X | X |  | X |  |  | X | [15 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co10 | Scoping | Tertiary | Post-construction, the working area will be reinstated to pre-existing condition as far as reasonably practical in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298 or latest relevant available guidance. | Construction | X |  | X | X |  | X | X | X | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) DCO Requirement 19 (Restoration of land used temporarily for construction) | Pre-construction of the connection works Within 12 months of completion of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co13 | PEIR | Tertiary | Where cable trenching or road widening of the construction accesses is required across perched or near-surface secondary A or B aquifers, measures will be implemented to ensure that groundwater quality is not affected and detailed within the Pollution Prevention Plan (PPP) (Co4) to prevent changes to chemical quality, and the use of thermally insulated Direct Current cables to prevent effects on groundwater temperature). Furthermore, measures to ensure that the cable trench does not become a conduit for groundwater flow will also be implemented (e.g. ensuring that backfill is sufficiently compacted and has the same transmissivity as adjacent undisturbed material). Appropriate measures will be identified following consultation with the Environment Agency and will be reported within the CoCP (Co124). This will be in line with the requirements of Section 23-25 of the Land Drainage Act 1991, or the latest relevant available guidance. | Construction | X | [5 empty] | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co14 | PEIR | Tertiary | A Construction Drainage Scheme will be developed for the temporary construction works, to ensure that existing land drainage is maintained during construction. Specific drainage measures for each area of land will be specified based on information identified and recorded by a Land Drainage Consultant prior to construction. The Construction Drainage Scheme will be developed in consultation with landowners, the Lead Local Flood Authority, Environment Agency and relevant Internal Drainage Board. | Construction | X |  | X | X |  |  | X | [17 empty] | DCO Requirement 12 (Surface and foul water drainage) | Pre-construction of the connection works | Lead local flood authority | Outline Onshore Infrastructure Drainage Strategy (Doc No. F2.6)
Co18 | PEIR | Secondary | HDD entry and exit points will be located at least 9 m away from surface watercourses and the onshore export cable will be installed at least 1.2 m beneath the bed of any watercourses. The optimal clearance depth beneath watercourses will be agreed with the relevant authorities prior to construction. Where Hornsea Four crosses sites of particular sensitivity (e.g. SSSIs or groundwater Inner Source Protection Zones (SPZs)) a hydrogeological risk assessment will be undertaken to inform a site specific crossing method statement which will also be agreed with the relevant authorities prior to construction. | Construction | X | [5 empty] | X |  |  |  |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co19 | PEIR | Tertiary | An Onshore Infrastructure Drainage Strategy will be developed for the permanent operational development along the onshore cable corridor and the onshore substation, and will include measures to ensure that existing land drainage is reinstated and maintained, and measures to limit discharge rates and attenuate flows such that pre-development run-off rates to surrounding land are retained. The Onshore Infrastructure Drainage Strategy will be developed in consultation with the Environment Agency, Lead Local Flood Authority and relevant Internal Drainage Board as appropriate. | Construction | X |  |  | X |  | X | X |  | X | [15 empty] | DCO Requirement 12 (Surface and foul water drainage) | Pre-operation of the connection works | Lead local flood authority | Outline Onshore Infrastructure Drainage Strategy (Doc No. F2.6)
Co25 | Scoping | Primary | The onshore export cable corridor will be completely buried underground for its entire length. No overhead pylons will be installed as part of the consented works for Hornsea Four. | Construction | X |  |  |  |  | X | X | X |  | X | [14 empty] | DCO Schedule 1, Part 1 Authorised Development | n/a | n/a | n/a
Co26 | Scoping | Primary | Where hedgerows require removal, this will be undertaken prior to topsoil removal and the width of hedge removed will be limited where practical. Removed hedges and trees will be replaced with locally appropriate native species. | Construction | X |  | X | X |  |  |  | X |  | X |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice); and; DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works Pre-construction of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2) Outline EMP (Doc No. F2.3)
Co27 | PEIR | Primary | Trees identified to be retained as per the Onshore Crossing Schedule will be fenced off and worked around. Where works close to trees that will remain in situ are required, techniques will be used to safeguard the root protection zone. | Construction | X |  | X | X | [5 empty] | X |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice); and; DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works Pre-construction of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2) Outline EMP (Doc No. F2.3)
Co28 | Scoping | Primary | Joint Bays will be completely buried, with the land above reinstated except where access will be required from ground level, e.g. via link box chambers and manholes. | Construction | X |  | X |  |  | X | X | X | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice); and; DCO Requirement 19 (Restoration of land used temporarily for construction) | Pre-construction of the connection works Within 12 months of completion of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co30 | PEIR | Secondary | A Landscape Management Plan will be developed in accordance with the outline Landscape Management Plan. The plan will include details of mitigation planting at the onshore substation site, including number, location and species. Details of management and maintenance of planting will be provided. Where practical, landscape mitigation planting will be established as early as possible in the construction phase. | Construction | X |  | X | X |  | X |  | X |  | X | [14 empty] | DCO Requirement 7 (Provision of landscaping) | Pre-construction of the connection works | Relevant Planning Authority | n/a
Co33 | Scoping | Tertiary | All vegetation requiring removal will be undertaken outside of the bird breeding season. If this is not possible, the vegetation requiring removal will be subject to a nesting bird check by a suitably qualified ECoW. If nesting birds are present, the vegetation will not be removed until the young have fledged or the nest failed. | Construction | X |  | X | X |  | X | [5 empty] | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3)
Co35 | PEIR | Secondary | Provision will be made for badger access in relevant construction areas, when work is not taking place in order to ensure normal movements as far as reasonably possible. Provision will be made to ensure avoiding the entrapment of any animals within relevant construction areas. Checks will be made prior to the start of any works to ensure no animals are trapped. Appropriate checks will be made as required by the ECoW. | Construction | X |  | X | X | [7 empty] | X | [12 empty] | DCO Requirement 16 (Code of construction practice); and; DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works Pre-construction of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2) Outline EMP (Doc No. F2.3)
Co36 | Scoping | Primary | Core working hours for the construction of the onshore components of Hornsea Four will be as follows: • Monday to Friday: 07:00 - 18:00 hours; • Saturday: 07:00 - 13:00 hours; • Up to one hour before and after core working hours for mobilisation (“mobilisation period”), i.e. 06:00 to 19:00 weekdays and 06:00 to 14:00 Saturdays; and • Maintenance period 13:00 to 17:00 Saturdays. Activities carried out during mobilisation and maintenance will not generate significant noise levels (such as piling, or other such noisy activities). In circumstances outside of core working practices, specific works may have to be undertaken outside the core working hours. ERYC will be informed in writing. | Construction | X |  | X | X | [6 empty] | X | X |  | X | [10 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co41 | Scoping | Primary | All HDD crossings will be undertaken by non-impact methods in order to minimise construction vibration beyond the immediate location of works. | Construction | X |  | X |  |  | X |  |  |  |  | X | [13 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2); Onshore Crossing Schedule (Doc No. A4.4.1)
Co43 | PEIR | Secondary | All temporary and permanent working areas of the onshore Export Cable Corridor (ECC), logistics compounds and the onshore substation site will be clearly marked and secured with appropriate fencing. | Construction | X | [7 empty] | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) (relevant to temporary fencing) DCO Requirement 11 (Fencing and other means of enclosure) (relevant to permeant fencing) | Pre-construction of the connection works Pre-construction of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2) | Agree
Co44 | RPSS | Primary | The Holderness Inshore Marine Conservation Zone (MCZ) will not be crossed by the offshore export cable corridor including the associated temporary works area. | Construction |  | X | [12 empty] | X | X | X | [7 empty] | DCO Schedule 1, Part 1 Authorised Development | n/a | n/a | DCO Works Plan - Offshore (Doc No. D1.4.1)
Co45 | RPSS | Primary | The Holderness Offshore Marine Conservation Zone (MCZ) will not be crossed by the offshore export cable corridor including the associated temporary works area. | Construction |  | X | [12 empty] | X | X | X | [7 empty] | DCO Schedule 1, Part 1 Authorised Development | n/a | n/a | DCO Works Plan - Offshore (Doc No. D1.4.1)
Co46 | RPSS | Primary | The offshore export cable corridor and the array will be routed to avoid any identified archaeological receptors pre construction, with buffers as detailed in the Marine Written Scheme of Investigation WSI. | Construction |  | X |  |  | X | [17 empty] | X |  | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 12(2) (Marine Written Scheme of Archaeological Investigation) | Pre-commencement of licensed activities | MMO | Outline Marine Written Scheme of Investigation (Doc No. F2.4)
Co48 | PEIR | Primary | Annex 1 habitats will be avoided where possible, informed through the undertaking of geophysical survey works pre-construction. This excludes features of Smithic Sands which at the time of application is not designated. | Pre-construction |  | X |  |  | X | [10 empty] | X | [8 empty] | DCO Schedule 11, Part 2 - Condition 12(1)(a) and; DCO Schedule 12, Part 2 - Condition 12(1)(a) (Pre-construction plans and documentation) | Pre-commencement of licensed activities | MMO | n/a
Co49 | RPSS | Primary | There will be no permanent High Voltage infrastructure installed above surface within 50m of residential properties and sub surface within 25m of residential properties. | Construction | X |  | X | X | [5 empty] | X | [14 empty] | DCO Requirement 6 (Detailed design approval onshore) | Pre-construction of the connection works | Relevant Planning Authority | Outline Design Vision Statement (A4.4.6)
Co57 | PEIR | Tertiary | Where offshore export cables must cross third party infrastructure, such as existing cables and pipelines, both the third-party asset and the installed cables will be protected. | Construction |  | X | [21 empty] | X | Crossing Agreements | n/a | n/a | n/a
Co61 | PEIR | Secondary | Prior to the commencement of works, the contractor (or project appointed Agricultural Liaison Officer) will document information on existing agricultural management and soil/land conditions. This will include soil condition surveys and intrusive soil survey trial pits to identify and describe the physical and nutrient characteristics of the existing soil profiles. | Pre-construction | X |  | X | X |  | X | [18 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co62 | PEIR | Secondary | Temporary access points off the highway will be installed to facilitate vehicular access from the road, and into the onshore cable corridor during construction. The access points will be constructed in line with the local authorities’ requirements, relevant appropriate standards and in accordance with the principles established in the Outline Construction Traffic and Travel Management Plan. | Construction | X |  | X | X | [9 empty] | X | [10 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co63 | PEIR | Primary | The haul road will be installed within the works area of the onshore Export Cable Corridor (ECC) to minimise impacts during construction on agricultural land. | Construction | X |  | X | X |  |  |  |  | X | [15 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co64 | Scoping | Tertiary | Topsoil and subsoil will be stored in separate stockpiles in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298 or the latest relevant available guidance. Any suspected or confirmed contaminated soils will be appropriately separated, contained and tested before removal (if required). | Construction | X |  | X | X |  | X | X |  |  | X |  |  | X | [11 empty] | DCO Requirement 16 (Code of construction practice) DCO Requirement 13 (Contaminated land and groundwater scheme) | Pre-construction of the connection works Pre-construction of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co65 | PEIR | Tertiary | A Site Waste Management Plan (SWMP) will be developed with consideration of the latest relevant available guidance. | Construction | X |  | X | X |  |  | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co68 | PEIR | Secondary | All logistics compounds will be removed and sites restored to their original condition when construction has been completed. | Construction | X |  | X | X |  | X | X |  | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) DCO Requirement 19 (Restoration of land used temporarily for construction) | Pre-construction of the connection works Within 12 months of completion of the connection works | Relevant Planning Authority Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co69 | PEIR | Secondary | Site lighting will only operate when required and will be directional to avoid unnecessary illumination. | Construction | X |  | X | X |  |  |  | X |  | X |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co76 | Scoping | Tertiary | Appropriate Personal Protective Equipment (PPE) will be used and relevant good working practices applied to avoid potential risk to human health from any potential ground contamination, in line with relevant available guidance. | Construction | X |  | X | X |  | X | [18 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co77 | Scoping | Tertiary | A contaminated land and groundwater scheme will be prepared to identify any contamination and any remedial measures which may be required. | Construction | X |  | X | X |  | X | X |  |  |  |  | X | [12 empty] | DCO requirement 13 (Contaminated land and groundwater scheme) | Pre-construction of the connection works | Relevant Planning Authority | n/a
Co78 | RPSS | Primary | Ponds will be avoided through micro-siting of the onshore export cable where practical. | Construction | X |  | X | X | [5 empty] | X |  | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3) | Disagree
Co79 | Scoping | Primary | Severance to PRoW will be temporary where possible, and appropriate temporary diversions, gated crossings and signage will be provided during construction. PRoW will be reinstated as soon as reasonably practical. Where permanent severance to PRoW is necessary, permanent diversions of such routes will be applied. | Construction | X |  | X | X |  |  |  |  | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co81 | Scoping | Tertiary | Where scour protection is required, MGN 543 (or latest relevant available guidance) will be adhered to with respect to changes greater than 5% to the under keel clearance. | Construction |  | X |  |  | X | [14 empty] | X | X |  |  | X | DCO Schedule 11, Part 2 - Condition 14 and; DCO Schedule 12, Part 2 - Condition 14 (Offshore safety management) | Pre-commencement of licensed activities | MMO | n/a
Co82 | Scoping | Tertiary | A Scour Protection Management Plan will be developed. It will include details of the need, type, quantity and installation methods for scour protection. | Construction |  | X |  |  | X | [9 empty] | X | [9 empty] | DCO Schedule 11, Part 2 - Condition 12(1)(e) and; DCO Schedule 12, Part 2 - Condition 12(1)(e) (Scour Protection Management Plan) | Pre-commencement of licensed activities | MMO | n/a
Co83 | Scoping | Primary | Where possible, cable burial will be the preferred option for cable protection. | Construction |  | X | [12 empty] | X | X | X |  |  | X | X |  | X |  | DCO Schedule 11, Part 2 - Condition 12(1)(h) and; DCO Schedule 12, Part 2 - Condition 12(1)(h) (Cable specification and installation plan) | Pre-commencement of licensed activities | MMO | n/a
Co84 | RPSS | Primary | Presence of sensitive habitats will be identified through a review of the latest available benthic datasets and pre-construction surveys. Wind turbine foundations and the offshore export cable will be micro-sited around annex one habitat wherever reasonably practicable (subject to agreement with the MMO) to an extent not resulting in a hazard for marine traffic and Search & Rescue capability. | Construction |  | X |  |  | X | [10 empty] | X | [8 empty] | DCO Schedule 11, Part 2 - Condition 12(1)(a) and; DCO Schedule 12, Part 2 - Condition 12(1)(a) (Pre-construction plans and documentation) | Pre-commencement of licensed activities | MMO | n/a
Co85 | PEIR | Primary | No more than a maximum of two foundations are to be installed simultaneously. | Construction |  |  |  |  | X | [11 empty] | X | X |  | X |  |  |  |  | DCO Schedule 11, Part 2 - Condition 12(1)(g) and; DCO Schedule 12, Part 2 - Condition 12(1)(g) (Marine mammal mitigation protocol) | Pre-commencement of licensed activities | MMO | Outline MMMP (Doc No. F2.5)
Co86 | RPSS | Primary | The offshore export cable corridor and cable landfall (below MHWS) will not cross the Greater Wash SPA, Flamborough & Filey Coast SPA and the Flamborough Head SAC. | Construction |  | X | [13 empty] | X |  |  | X | [5 empty] | DCO Schedule 1, Part 1 Authorised Development | n/a | n/a | DCO Works Plan - Offshore (Doc No. D1.4.1)
Co87 | PEIR | Primary | Proposed developable area has been selected from the larger Hornsea Four Agreement for Lease (AfL) area to avoid areas with the highest concentrations of birds (kittiwake, gannet an guillemot) that are more likely to be displaced by the construction activities, and birds that are more likely to fly at heights that brings them within the rotor swept zone and hence at risk of collision. | Construction |  |  |  |  | X | [13 empty] | X | [5 empty] | DCO Schedule 1, Part 1 Authorised Development | n/a | n/a | DCO Works Plan - Offshore (Doc No. D1.4.1)
Co88 | Scoping | Tertiary | Construction and operational maintenance vessels (e.g. CTVs) will avoid high concentrations of rafting red-throated diver. | Construction |  | X |  |  | X | [13 empty] | X | [5 empty] | DCO Schedule 11, Part 2 - Condition (12)(d)(v) and; DCO Schedule 12, Part 2 - Condition (12)(d)(v) (Vessel Management Plan) | Pre-commencement of licensed activities | MMO | n/a
Co89 | Scoping | Tertiary | Advance warning and accurate location details of construction, maintenance and decommissioning operations, associated Safety Zones and advisory passing distances will be given via Notices to Mariners and Kingfisher Bulletins). | Construction |  | X |  |  | X | [14 empty] | X | X |  |  | X | DCO Schedule 11, Part 2 - Condition 6(8) and; DCO Schedule 12, Part 2 - Condition 6(8) (Notifications and inspections) | Pre-commencement of licensed activities | n/a | n/a
Co90 | Scoping | Tertiary | Ongoing liaison with fishing fleets will be maintained during construction, maintenance and decommissioning operations via an appointed Fisheries Liaison Officer and Fishing Industry Representative. | Construction |  | X |  |  | X | [14 empty] | X |  |  |  |  | DCO Schedule 11, Part 2 - Condition 12(1)(d)(vi) and; DCO Schedule 12, Part 2 - Condition 12(1)(d)(vi) (Project environmental management and monitoring plan) | Pre-commencement of licensed activities | MMO | n/a
Co93 | RPSS | Tertiary | Aids to navigation (marking and lighting) will be deployed in accordance with the latest relevant available standard industry guidance and as advised by Trinity House, MCA and Civil Aviation Authority (CAA) and MoD as appropriate. This will include a buoyed construction area around the array area and the HVAC booster station in consultation with Trinity House. | Construction |  | X |  |  | X | [14 empty] | X | X | X |  | X | DCO Schedule 11, Part 2 - Condition 7 and; DCO Schedule 12, Part 2 - Condition 7 (Aids to navigation) DCO Schedule 11, Part 2 - Condition 12(1)(j) and; DCO Schedule 12, Part 2 - Condition 14(1)(j) (Aid to navigation management plan) | n/a Pre-commencement of licensed activities | n/a MMO | n/a n/a
Co94 | RPSS | Tertiary | The United Kingdom Hydrographic Office will be notified of both the commencement (within two weeks), progress and completion of offshore construction works (within two weeks) to allow marking of all installed infrastructure on nautical charts. | Construction |  | X |  |  | X | [14 empty] | X | X |  |  | X | DCO Schedule 11, Part 2 - Condition 6(10) and; DCO Schedule 12, Part 2 - Condition 6(10) (Notifications and inspections) | n/a | n/a | n/a
Co95 | Scoping | Tertiary | A fisheries co-existence and liaison plan will be prepared prior to the commencement of construction. | Construction |  | X |  |  | X | [14 empty] | X |  |  |  |  | n/a | n/a | n/a | n/a
Co96 | Scoping | Tertiary | The project commits to agreeing layout principles with MCA, which will include maintaining at least one line of symmetry/ orientation in turbine layout. | Construction |  |  |  |  | X | [15 empty] | X |  |  | X | DCO Schedule 11, Part 2 - Condition 12(1)(a) and; DCO Schedule 12, Part 2 - Condition 12(1)(a) (Pre-construction plans and documentation) | Pre-commencement of licensed activities | MMO | Layout Principles (A4.4.7)
Co98 | Scoping | Tertiary | Monitoring of vessel traffic for the duration of the construction period. | Construction |  | X |  |  | X | [15 empty] | X |  |  | X | DCO Schedule 11, Part 2 - Condition 17(2)(b) and; DCO Schedule 12, Part 2 - Condition 17(2) (Construction Monitoring) | n/a | n/a | n/a | Agree
Co99 | Scoping | Tertiary | Hornsea Four will ensure compliance with MGN543 where appropriate. | Construction |  | X |  |  | X | [14 empty] | X | X | X |  | X | DCO Schedule 11, Part 2 - Condition 14 and; DCO Schedule 12, Part 2 - Condition 14 (Offshore safety management) | Pre-commencement of licensed activities | MMO | n/a
Co102 | Scoping | Tertiary | The Defense Geographic Organisation will be informed of the locations, heights and lighting status of the wind turbines, including estimated and actual dates of construction and the maximum height of any construction equipment to be used, prior to the start of construction, to allow inclusion on Aviation Charts. | Construction |  |  |  |  | X | [16 empty] | X |  | X | DCO Schedule 11, Part 2 - Condition 6 and; DCO Schedule 12, Part 2 - Condition 6 (Notifications and Inspections) | Pre-commencement of licensed activities | n/a | n/a
Co107 | Scoping | Tertiary | Crossing and proximity agreements with known existing pipeline and cables operators will be sought. | Construction |  | X |  |  | X | [18 empty] | X | Secured by commercial agreements with pipeline and cable operators. | n/a | n/a | n/a | Agree
Co108 | Scoping | Tertiary | A Vessel Management Plan (VMP) will be developed pre-construction which will determine vessel routing to and from construction areas and ports to minimise encounters with marine mammals. | Construction |  | X |  |  | X | [12 empty] | X | [5 empty] | X | DCO Schedule 11, Part 2 - Condition 12(1)(d)(v) and; DCO Schedule 12, Part 2 - Condition 12(1)(d)(v) (Vessel management plan) | Pre-commencement of licensed activities | MMO | n/a
Co110 | Scoping | Tertiary | A piling Marine Mammal Mitigation Protocol (MMMP), will be implemented during construction and will be developed in accordance with JNCC (2010) guidance. The piling MMMP will include details of soft starts to be used during piling operations with lower hammer energies used at the beginning of the piling sequence before increasing energies to the higher levels. | Construction |  |  |  |  | X | [11 empty] | X | X | [6 empty] | DCO Schedule 11, Part 2 - Condition 12(1)(g) and; DCO Schedule 12, Part 2 - Condition 12(1)(g) (Marine mammal mitigation protocol) | Pre-commencement of licensed activities | MMO | Outline MMMP (Doc No. F2.5)
Co111 | Scoping | Tertiary | A Marine Pollution Contingency Plan (MPCP) will be developed. This MPCP will outline procedures to protect personnel working and to safeguard the marine environment and mitigation measures in the event of an accidental pollution event arising from offshore operations relating to Hornsea Four. The MPCP will also include relevant key emergency contact details | Construction |  | X |  |  | X | [10 empty] | X | X | X |  | X |  |  |  |  | DCO Schedule 11, Part 2 - Condition 12(1)(d)(i) and; DCO Schedule 12, Part 2 - Condition 12(1)(d)(i) (Marine pollution contingency plan) | Pre-commencement of licensed activities | MMO | n/a
Co113 | Scoping | Tertiary | A Decommissioning Marine Mammal Mitigation Protocol (MMMP), will be implemented during decommissioning. The Decommissioning MMMP will include measures to ensure the risk of permanent threshold shift (PTS) to marine mammals is negligible and will be in line with the latest relevant available guidance. | Decommissioning |  | X |  |  | X | [11 empty] | X | X | [6 empty] | A separate Marine License will be applied for at the point of decommissioning which will include Conditions relevant to minimising impacts on marine mammals where appropriate. | n/a | MMO | n/a
Co114 | Scoping | Tertiary | Good practice air quality management measures will be applied where it is relevant, as described in Institute of Air Quality Management (IAQM) Guidance on the Assessment of Dust from Demolition and Construction 2014, version 1.1, or latest relevant available guidance. | Construction | X |  | X | X |  |  |  |  | X |  |  | X | X | [11 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co119 | PEIR | Secondary | In areas of confirmed presence, or potential for great crested newt (i.e. within 250 m of an identified great crested newt pond) appropriate exclusion fencing will be erected and working areas ‘trapped out’ prior to the commencement of relevant onshore construction works, in line with Great crested newt mitigation guidelines, English Nature, 2001 or the latest available relevant guidance.. | Construction | [11 empty] | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3)
Co120 | PEIR | Secondary | Habitat manipulation will be undertaken in order to discourage reptiles from the working area(s). A qualified ecologist will undertake a search of all working areas identified as being suitable for reptiles. Any reptiles found within the working area will be relocated into suitable adjacent habitat. | Construction | [11 empty] | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3)
Co122 | PEIR | Secondary | Prior to the commencement of construction activities and due to the mobility of species, pre-construction surveys will be undertaken by the ECoW to ensure the site conditions remain unchanged to that previously recorded. Should site conditions have changed and/or species moved into the working area(s), the ECoW will undertaken additional surveys in accordance with the species specific guidance. | Construction | [11 empty] | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3)
Co123 | Scoping | Tertiary | Based on noise modelling results, where noise has the potential to cause significant adverse effects, mufflers and acoustic barriers will be used where HDD is being undertaken. | Construction | X |  | X | X |  |  |  |  | X |  | X | X | [12 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co124 | Scoping | Tertiary | A Code of Construction Practice (CoCP) will be developed in accordance with the outline CoCP. The outline CoCP will include measures to reduce temporary disturbance to residential properties, recreational users and existing land users. | Construction | X |  | X | X |  | X | X | X | X | X | X | X | X | X | [10 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co127 | Scoping | Tertiary | An Onshore Decommissioning Plan will be developed prior to decommissioning. The Onshore Decommissioning Plan will include provisions for the removal of all onshore above ground infrastructure and the decommissioning of below ground infrastructure and details relevant to pollution prevention and avoidance of ground disturbance. The Onshore Decommissioning Plan will be in line with the latest relevant available guidance. | Decommissioning | X |  | X | X |  | X | X |  | X | X |  | X | [12 empty] | DCO Requirement 21 (onshore decommissioning) | Within three months of commercial operation | Relevant Planning Authority | n/a
Co133 | RPSS | Primary | The onshore export cable corridor (ECC) will be routed to avoid residential receptors by at least 50 m. | Construction | X | [7 empty] | X | X | X |  | X | [11 empty] | DCO Works Plan - Onshore | n/a | n/a | DCO Works Plan - Onshore (Doc No. D1.4.2)
Co134 | RPSS | Primary | Cable installation works at the landfall area will be located at least 200 m from residential receptors. | Construction |  |  | X | [5 empty] | X | X | X |  | X | [11 empty] | DCO Works Plan - Onshore | n/a | n/a | DCO Works Plan - Onshore (Doc No. D1.4.2)
Co135 | RPSS | Primary | Temporary construction highway access points along the onshore export cable corridor (ECC) will be located at least 150m from residential receptors, with the exception of two receptors: Bridge Farm Holiday Cottages, Brigham, Driffield, and a receptor off the A1035 Malton Road, Beverley. | Construction | X | [8 empty] | X | X |  | X | [11 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co137 | Scoping | Tertiary | HGV movements associated with operation and planned maintenance of the onshore infrastructure will operate only between the hours of 0700 – 2300. HGV movements may however be subject to unscheduled maintenance activities outside these hours. In this event the council will be informed via writing. | Operation and maintenance | X |  | X | X | [6 empty] | X | [13 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2) | Agree
Co138 | Scoping | Primary | Lower air draught of wind turbines will be a minimum of 35 m above Mean Sea Level (MSL) | Operation and maintenance |  |  |  |  | X | [13 empty] | X | [5 empty] | DCO Requirement 2(2)(c) (Detailed offshore design parameters) DCO Schedule 11, Part 2 - Condition 1(2)(c) (Design parameters) | n/a | n/a | n/a | Agree
Co139 | Scoping | Secondary | Safety zones of up to 500m will be applied during construction, maintenance and decommissioning phases. Where appropriate, guard vessels will also be used to ensure adherence with Safety Zones or advisory passing distances, as defined by risk assessment, to mitigate any impact which poses a risk to surface navigation during construction, maintenance and decommissioning phases. Such impacts may include partially installed structures or cables, extinguished navigation lights or other unmarked hazards. | Construction |  | X |  |  | X | [14 empty] | X | X |  |  | X | Application for safety zones to be made post consent under ’The Electricity (Offshore Generating Stations) (Safety Zones) (Applications Procedures and Control of Access) Regulations 2007 (SI No 2007/1948)’. Safety zones required are also detailed within the Project Description. | n/a | n/a | Safety Zone Statement (to be provided at Application)
Co140 | RPSS | Primary | Archaeological exclusion zones (AEZs) will be established in the Marine WSI in accordance with the outline Marine WSI (document reference F2.4), to protect any known / identified marine archaeological receptors. | Construction |  | X |  |  | X | [17 empty] | X |  | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 12(2) (Marine Written Scheme of Archaeological Investigation) | Pre-commencement of licensed activities | MMO | Outline Marine Written Scheme of Investigation (Doc No. F2.4)
Co141 | Scoping | Tertiary | A Marine Written Scheme of Archaeological Investigation (WSI) will be developed in accordance with the Outline Marine WSI. The Marine WSI will include the implementation of a protocol for Archaeological Discoveries in accordance with ‘Protocol for Archaeological Discoveries: Offshore Renewables Projects’ (The Crown Estate, 2014). | Construction |  | X |  |  | X | [17 empty] | X |  | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 12(2) (Marine Written Scheme of Archaeological Investigation) | Pre-commencement of licensed activities | MMO | Outline Marine Written Scheme of Investigation (Doc No. F2.4)
Co143 | PEIR | Secondary | The landfall site will avoid the Barmston Main Drain. | Construction | X |  | X |  |  | X | X | [17 empty] | DCO Works Plan - Onshore | n/a | n/a | DCO Works Plan - Onshore (Doc No. D1.4.2)
Co144 | LIE | Tertiary | A Construction Traffic Management Plan (CTMP) will be developed in accordance with the outline CTMP to be submitted with the DCO application. The CTMP will set standards and procedures for: 1. Managing the numbers and routing of HGVs during the construction phase; 2. Managing the movement of employee traffic during the construction phase; 3. Details of localised road improvements necessary to facilitate safe use of the existing road network; and 4. Details of measures to manage the safe passage of HGV traffic via the local highway network | Construction | X |  | X | [7 empty] | X |  |  | X | [10 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co145 | LIE | Primary | Views of Beverley Minster from the A1079 will not be obstructed by the siting of the onshore substation, | Pre-construction |  |  |  | X |  |  |  | X |  | X | [14 empty] | DCO Requirement 6 (Detailed design approval onshore) | Pre-construction of the connection works | Relevant Planning Authority | Outline Design Vision Statement (A4.4.6)
Co147 | LIE | Tertiary | Appropriate liaison will take place with the Internal Drainage Board during construction. | Construction | X |  | X | X |  |  | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co150 | LIE | Primary | A new access will be taken directly from the A1079, to route construction traffic away from Cottingham and Dunswell. | Construction |  |  |  | X |  |  |  | X | [5 empty] | X | [10 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co151 | LIE | Primary | No above ground infrastructure associated with Hornsea Four will obstruct the view from St Mary's Church Cottingham to Beverley Minister through considered design of the OnSS and site selection. | Pre-construction | X |  |  | X |  |  |  | X |  | X | [14 empty] | DCO Requirement 6 (Detailed design approval onshore) | Pre-construction of the connection works | Relevant Planning Authority | Outline Design Vision Statement (A4.4.6)
Co157 | PEIR | Secondary | Fences, walls, ditches and drainage outfalls will be retained along the onshore export cable corridor and landfall, where possible. Where it is not possible to retain them, any unavoidable damage will be repaired and reinstated as soon as reasonably practical. | Construction | X |  | X | X |  |  | X |  |  | X |  | X | [12 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co158 | PEIR | Secondary | Impacts on the English Coast Path national route will be minimised by avoiding impacts through site design and phasing within working constraints for the landfall construction. In addition, Co79 will be applied to the English Coast Path national route. | Construction |  |  | X | [5 empty] | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co159 | PEIR | Secondary | Operational noise from the onshore substation will be at a noise level no greater than 5dB above the representative background (LA90,T) during the day time and night at the Nearest Sensitive Receptors, as stated within the onshore noise assessment (document reference A3.8). | Operation and maintenance |  |  |  | X |  |  |  | X |  |  | X | X | [12 empty] | DCO requirement 20 (Control of noise during operational phase) | Pre-construction of Works Nos. 7 | Relevant Planning Authority | n/a
Co160 | PEIR | Secondary | An Onshore Archaeological Written Scheme of Investigation (WSI) will be developed in line with an Outline Onshore Archaeological Written Scheme of Investigation (WSI). The onshore WSI will detail the survey and archaeological mitigation requirements in advance of and during construction. | Construction | X |  | X | X |  |  |  | X | [16 empty] | DCO requirement 15 (Onshore archaeology) | Pre-construction of the connection works | Relevant Planning Authority | n/a
Co162 | PEIR | Secondary | Non-intrusive surveys (including Priority Archaeological Geophysical Survey, Geoarchaeological Desk Based Review and Aerial Photographic and Lidar Assessment) will be undertaken to identify and establish areas of buried archaeological remains and surviving historic earthworks. Where possible, the results will be used to inform design and minimise impacts on buried archaeological remains and historic earthworks through route refinement. | Pre-construction | X |  |  | X |  |  |  | X | [14 empty] | X |  | DCO requirement 15 (Onshore archaeology) | Pre-construction of the connection works | Relevant Planning Authority | n/a
Co165 | PEIR | Secondary | Where PRoWs are required to be closed during the construction of the onshore connection works, they will not be closed for any longer than three months at any one time, or for six months in total over the whole construction period. Where closures are required for longer period, East Riding of Yorkshire Council will be informed in writing. | Construction | X |  | X | X |  |  |  |  | X | X | [14 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co166 | PEIR | Secondary | A offshore geophysical survey (including a UXO survey) will be undertaken prior to construction and will be subject to a full archaeological review in consultation with Historic England. | Pre-construction | X |  | X | X | [18 empty] | X |  | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 12(2) (Marine Written Scheme of Archaeological Investigation) | Pre-commencement of licensed activities | MMO | Outline Marine Written Scheme of Investigation (Doc No. F2.4)
Co167 | PEIR | Secondary | A offshore geotechnical survey will be undertaken prior to construction, including a staged geoarchaeological assessment and analysis of geotechnical data inclusive of publication, in consultation with Historic England. | Pre-construction | X |  | X | X | [18 empty] | X |  | DCO Schedule 11, Part 2 - Condition 12(2) and; DCO Schedule 12, Part 2 - Condition 12(2) (Marine Written Scheme of Archaeological Investigation) | Pre-commencement of licensed activities | MMO | Outline Marine Written Scheme of Investigation (Doc No. F2.4)
Co168 | PEIR | Tertiary | An Ecological Management Plan (EMP) will be developed in accordance with the outline Ecological Managemtn Plan (OEMP), which will include details of onshore ecology and nature conservation pre-construction, construction, post-construction and any long-term mitigation and management (where applicable). The OEMP includes, but is not limited to: habitats, birds, bats, badgers, otters, water voles, reptiles, great crested newts, terrestrial invertebrates, and other protected or notable species where relevant. The OEMP will be developed in consultation with the relevant responsible authorities. | Construction |  |  | X | [8 empty] | X | [12 empty] | DCO Requirement 9 (Ecological Management Plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline EMP (Doc No. F2.3)
Co169 | PEIR | Secondary | Piling at the Onshore Substation (OnSS) will not be undertaken within 180m of any noise sensitive receptors. | Construction |  |  | X | [7 empty] | X | [13 empty] | DCO Requirement 6 (Detailed design approval onshore) | Pre-construction of the connection works | Relevant Planning Authority | Outline Design Vision Statement (A4.4.6)
Co170 | PEIR | Secondary | Joint bays and link boxes will be minimum 20 m away from main rivers. | Construction | X | [5 empty] | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co171 | PEIR | Secondary | HGVs will avoid travel through Foston on the Wolds. | Construction | X |  | X | X | [9 empty] | X | [10 empty] | DCO Requirement 17 (Construction traffic management plan) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co172 | PEIR | Secondary | The bed and banks of watercourses will be instated to their pre-construction condition following the removal of any temporary structures. | Construction | X | [5 empty] | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co175 | PEIR | Secondary | A pre and post construction condition survey will be undertaken at each of the crossing location on primary and secondary watercourses where infrastructure (e.g. A Bailey bridge) is emplaced upon banks. | Construction | X | [5 empty] | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co176 | PEIR | Tertiary | A Cable Specification and Installation Plan will be produced prior to construction of the offshore export cable which will include; details of cable burial depths; a detailed cable laying plan which ensures safe navigation is not compromised; details of cable protection for each cable crossing; and proposals for monitoring of offshore cable. | Construction |  | X | [18 empty] | X |  |  |  | DCO Schedule 11, Part 2 - Condition 12(1)(h) and; DCO Schedule 12, Part 2 - Condition 12(1)(h) (Cable specification and installation plan) | Pre-commencement of licensed activities | MMO | n/a
Co177 | PEIR | Tertiary | Hornsea Four vessels will comply with MGN 372 (Merchant and Fishing) Offshore Renewable Energy Installations (OREIs): Guidance to Mariners Operating in the Vicinity of UK OREIs (MCA, 2008) or the latest relevant available guidance where appropriate. | Construction |  | X |  |  | X | [15 empty] | X |  |  |  | n/a | n/a | n/a | n/a
Co178 | PEIR | Secondary | Hornsea Four will undertake further consultation with Regular Operators as part of the formal consultation process | n/a |  | X |  |  | X | [15 empty] | X |  |  |  | Ongoing Consultation with operators of deviated routes to secure commitments going forward as part of the DCO process. | n/a | n/a | n/a
Co179 | PEIR | Secondary | Hornsea Four will ensure marine coordination with the Marine Helicopter Coordination Centre (MHCC). | Construction |  | X |  |  | X | [15 empty] | X |  |  |  | n/a | n/a | n/a | n/a
Co180 | PEIR | Tertiary | The following guidance will be followed where appropriate; 'Recommendations For Fisheries Liaison: Best Practice' guidance for offshore renewable developers (FLOWW, 2006 and 2014; BERR, 2008). | Construction |  | X |  |  | X | [14 empty] | X |  |  |  |  | n/a | n/a | n/a | n/a
Co181 | PEIR | Tertiary | An Offshore Decommissioning Plan will be developed prior to decommissioning. | Decommissioning |  | X |  |  | X | [9 empty] | X | X | X | X | X | X | X | X | X | X | DCO Schedule 11, Part 1(6) and; DCO Schedule 12, Part 1(6) (General Provisions) | Pre-commencement of decommissioning | Secretary of State | n/a
Co182 | PEIR | Secondary | Hornsea Four will undertake further consultation with NATS and the Civil Aviation Authority (CAA) as part of the formal consultation process. | n/a |  | X |  |  | X | [16 empty] | X |  |  | n/a | n/a | n/a | n/a
Co183 | PEIR | Secondary | Where possible the design of all temporary access tracks will replicate or be as consistent with existing ground levels as possible, to limit any effects on future flood risk. | Construction | X |  | X | X |  |  | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)
Co184 | PEIR | Secondary | Where the permanent access track to the OnSS may be required to pass over an existing watercourse, the crossing will be appropriately designed to maintain existing ground elevations to ensure continued floodplain capacity and/or flow conveyance, where possible. | Construction |  |  |  | X |  |  | X | [17 empty] | DCO Requirement 16 (Code of construction practice) | Pre-construction of the connection works | Relevant Planning Authority | Outline CoCP (Doc No. F2.2)

## 5.RPSS & Scoping Change Log
5. RPSS & Scoping Change Log
Commitment Reference | Commitment Stage | Hornsea Four Commitment | Explanation of the change
Co1 | RPSS | All natural watercourses including main rivers and ordinary watercourses (not artificial drainage ditches, flood defences), main roads and railways will be crossed by HDD or other trenchless technology where technically practical. All main rivers, Interal Drainage Board (IDB) maintained drains, main roads and railways will be crossed by HDD or other trenchless technology as set out in the Onshore Crossing Schedule. Where HDD technologies are not practical, the crossing of ordinary watercourses may be undertaken by open cut methods. In such cases, temporary measures will be employed to maintain flow of water along the watercourse. | Co1 has been updated to include the latest PEIR information. The Commitment now notes that a Onshore Crossing Schedule is provided which includes the details of each crossing.
Co2 | RPSS | Where practical The following sensitive sites will be avoided by the permanent project footprint: Listed Buildings (580 sites), Registered Parks and Gardens (Thwaite Hall and Risby Hall), Scheduled Monuments (30 sites), Conservation Areas (19 sites), non-designated built heritage assets (368 sites) and Ancient Woodland (10 sites). Please refer to PEIR Volume 6, Annex 6.5.1 Appendix B Designated Assets Gazetteer for detailed lists of designated heritage assets that are avoided by Hornsea Four. With the exception of River Hull Headwaters SSSI, sensitive sites have been avoided. Please refer to PEIR Volume 6, Annex 3.1: Extended Phase 1 Habitat Survey Report for details.SSSI Units, Ancient woodland, areas of consented development, areas of historic landfill and other known areas of potential contamination, RSPB reserves, Local Nature Reserves, Local Wildlife Sites, Yorkshire Wildlife Trust Sites, National Trust Land, Listing Buildings, and Scheduled Monuments. Where possible, unprotected areas of woodland, mature, and protected trees (e.g. veteran trees) shall also be avoided or micro sited around. | Co2 has been updated to include the latest PEIR information, so Co2 now provides details of some specific sensitive sites which will be avoided, and details any relevent exceptions.
Co7 | Scoping | The temporary construction working area will typically associated with onshore export cable corridor will be 80m working width along the underground cable route to minimise the construction footprint, except the Network Rail Crossing near Beswick where the footprint is extended to 120m to facilitate HDD of the railway line. other crossings may expand this default to greater than 80m (HDD and local factors, over small lengths. The permanent width onshore export cable corridor width will be 60m except the Network Rail Crossing near Beswick where the footprint is extended to 120m to facilitate HDD of the railway line. | Co7 has been updated to make it clearer. The width of the permanent and temporary ECC have not been changed. Further information has been added to the commitment to incude details of locations where the footprint is extended (i.e at the Network Rail Crossing near Beswick).
Co10 | Scoping | Post-construction, the working area will be reinstated to pre-existing condition as far as reasonably practical in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298 or latest relevant available guidance. | Co10 has been updated to state that the latest guidance will be followed. No further information has been changed.
Co22 | Scoping | The following applies to both construction and operation: Refuelling of machinery will be undertaken within designated areas where spillages can be easily contained. Machinery will be routinely checked to ensure it is in good working condition. Any tanks and associated pipe work containing oils and fuels will be double skinned and be provided with intermediate leak detection equipment. Areas at risk of spillage, such as vehicle maintenance areas and hazardous substance stores (including fuel, oils and chemicals) will be bunded and carefully sited to minimise the risk of hazardous substances entering the drainage system or the local watercourses. Additionally the bunded areas will have impermeable bases to limit the potential for migration of contaminants into groundwater following any leakage/spillage. Bunds used will store fuel, oil etc. to have a 110% capacity. Disturbance to areas close to watercourses reduced to the minimum necessary for the work. Excavated material will be placed in such a way as to avoid any disturbance of areas near to the banks of watercourses and any spillage into the watercourses. Construction materials will be managed in such a way as to effectively minimise the risk posed to the aquatic environment. All plant machinery and vehicles will be maintained in a good condition to reduce the risk of fuel leaks. Drainage works to be constructed to relevant statutory guidance and approved via the Lead Local Flood Authority prior to the commencement of construction. Consultation with the Environment Agency to be ongoing throughout the construction period to promote best practice and to implement proposed mitigation measures. | Co22 detailed measures relevant to prevention of pollution. This Commitment has been removed and a singe commitment added to produce a Pollution Prevention Plan (Co4). The Pollution Prevention Plan will form part of the CoCP and relevant details are provided within the outline CoCP (document reference F2.2). Measures relating to contamination are contained within Co77. Co22 has therefore been removed, to streamline the commitments presented.
Co25 | Scoping | The onshore export cable route corridor will be completely buried underground for its entire length. No overhead pylons will be installed at any point during the project as part of the consented works for Hornsea Four. | Co25 has been updated to make it clearer. The previously named export cable route is now named the export cable corridor. No information has been changed.
Co26 | Scoping | Hedgerows and vegetation will be retained where possible. Where it is not possible to retain them, hedgerows will be removed prior to topsoil removal. The width of hedge and vegetation removed will be limited where practical. Where hedgerows require removal, this will be undertaken prior to topsoil removal and the width of hedge removed will be limited where practical. Removed hedges and trees will be replaced with locally appropriate native species. | Co26 has been updated with the latest PEIR information. It now states that Hornsea Four will replace any removed hedges and trees with locally appropriate native species.
Co28 | Scoping | Joint Bays will be completely buried, with the land above reinstated excepting link box chambers where access will be required from ground level, e.g. via link box chambers and manholes. | Co28 has been updated to make it clearer. No information has been changed.
Co33 | Scoping | Where removal of vegetation has to be undertaken during the bird breeding season, vegetation will be checked by a suitably qualified ecologist and where nests are present, the vegetation will not be removed until the chicks have fledged. All vegetation requiring removal will be undertaken outside of the bird breeding season. If this is not possible, the vegetation requiring removal will be subject to a nesting bird check by a suitably qualified ECoW. If nesting birds are present, the vegetation will not be removed until the young have fledged or the nest failed. | Co33has been updated to make it clearer that vegetation removal will be undertaken outside of bird breeding season where possible.
Co34 | Scoping | Where HDD technologies are not required or practical, the crossing of drainage ditches may be undertaken by open cut methods and / or the installation of temporary culverts or bridges to allow water to continue flowing. This will be in line with the appropriate advice and guidance notes. advice notes, guidance documents and additional information including Environment Agency Pollution Prevention Guidelines (PPGs) will be adhered to, particularly: • PPG01 General Guide to the Prevention of Water Pollution; • PPG02 Above Ground Oil Storage Tanks; • PPG04 Disposal of Sewage where no Mains Drainage is Available; • PPG05: Works in, Near or Liable to Affect Watercourses; • PPG06: Working at Construction and Demolition Sites; • PPG08 Safe Storage and Disposal of Used Oils; • PPG21: Pollution Incident Response Planning; and • Pollution Prevention: Major Pipeline. | Co34 had details relevant to methods that may be used where HDD is not possible. Measures relating to HDD, and other crossing techniques are now contained within Co1. Co34 also detailed measures relevant to prevention of pollution. This Commitment has been removed and a singe commitment added to produce a Pollution Prevention Plan (Co4). The Pollution Prevention Plan will form part of the CoCP and relevant details are provided within the outline CoCP (document reference F2.2). Measures relating to contamination are contained within Co77. Co34 has therefore been removed, to streamline the commitments presented.
Co36 | Scoping | Core working hours for the construction of the onshore components of Hornsea Four will be as follows: • Monday to Friday: 07:00 - 18:00 hours; • Saturday: 07:00 - 13:00 hours; • Up to one hour before and after core working hours for mobilisation (“mobilisation period”), i.e. 06:00 to 19:00 weekdays and 06:00 to 14:00 Saturdays; and • Maintenance period 13:00 to 17:00 Saturdays. Activities carried out during mobilisation and maintenance will not generate significant noise levels (such as piling, or other such noisy activities). In circumstances outside of normal working practices, specific works may have to be undertaken outside the normal working hours. such as: • Horizontal Directional Drilling (HDD) or other trenchless construction operations which may require 24 hour machinery operation, dependent on the ground conditions; • Remedial works, for example in the event of severe weather; • Delivery of electrical infrastructure; • Jointing operations along the cable route; and • Security of sites and protection of open assets. We will inform ERYC in writing. | This works that may be conducted outside of normal working practices have been removed, and are instead listed in the Outline CoCP.
Co41 | Scoping | All HDD trenchless crossings will be undertaken by non-impact methods and, as such, in order to minimise construction vibration and as such, construction vibration will be unlikely to be significant beyond the immediate location of works. No blasting is anticipated. | It is too early to state whether blasting will be required for HDD crossing methods so this has been removed from the commitment.
Co44 | RPSS | The Holderness Inshore Marine Conservation Zone (MCZ) (designated for Intertidal sand and muddy sand, Moderate energy circalittoral rock, High energy circalittoral rock, Subtidal coarse sediment, Subtidal mixed sediments, Subtidal sand, Subtidal mud, and Spurn head (subtidal)) will be avoided by marine ECR not be crossed by the offshore export cable corridor including the associated temporary works area. | Co44 has remved the explanation of the MCZ, as this information is provided in the DCO Works Plan. It also now states that the temporary works area will not cross the Holderness Inshore MCZ. Furthermore, the previously named export cable route is now named the export cable corridor.
Co45 | RPSS | The Holderness Offshore Marine Conservation Zone recommended MCZ (rMCZ)(proposed to be designated for North Sea Glacial Tunnel valleys, Subtidal coarse sediment, Subtidal sand, Subtidal mixed sediments and Ocean Quahog (Arctica islandica)) will be avoided by marine ECR. not be crossed by the offshore export cable corridor including the asscoiated temporary works area. marine ECR. | Co45 has remved the explanation of the MCZ, as this information is provided in the DCO Works Plan. It also now states that the temporary works area will not cross the Holderness Inshore MCZ. Furthermore, the previously named export cable route is now named the export cable corridor.
Co46 | RPSS | The offshore export cable corridor marine ECC and the (including WTGs and inter-array cables) will be routed so as to avoid any identified archaeological receptors known wrecks pre construction, with buffers as detailed in the Marine Written Scheme of Investigation WSI. (with a buffer of 50m around the wreck), further refined following high-resolution geophysical survey post-consent. | An Outline Marine WSI has been provided which includes full details of associated buffers, so it has been removed from here.
Co64 | Scoping | During construction of the cable trenches, the topsoil and subsoil will be stripped and stored on site within the temporary working area corridor of the Hornsea Four onshore export cable corridor.The Topsoil and subsoil will be stored in separate stockpiles in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298 or the latest relevant available guidance. Any suspected or confirmed contaminated soils will be appropriately separated, contained and tested before removal (if required). No material will be stockpiled within the floodplain of any watercourse. | Co64 has been update to remove reference to storage of topsoil and subsoil as this detail is set out within the Project Description. It is not possible to commit to stockpiling on a floodplain, as it is unknown where flooding will take place in the future.
Co76 | Scoping | Potential risks to human health from any encountered (unexpected) ground contamination will be avoided by the use of Appropriate Personal Protective Equipment (PPE) will be used and relevant good working practices applied to avoid potential risk to human health from any potential ground contamination, in line with relevent available guidance. and by adopting appropriate working practices will be adopted | Co76 has been updated to make it clearer. Appropriate good working practices have been removed, and will be detailed in the CoCP.
Co77 | Scoping | A contaminated land and groundwater scheme will be prepared to identify any contamination and any remedial measures which may be required.encountered during the construction phase which would be subject to appropriate risk assessment and if necessary, either removed, treated and/ or mitigated as part of the project. | Co77 has been updated to align with the draft DCO which includes a requirement to develop a Contaminated land and groundwater scheme. This scheme will ensure contamination is dealt with apprpriately and remidated where required.
Co78 | RPSS | Micro-siting will be undertaken during detailed design to avoid all ponds if practical. Ponds will be avoided through micro-siting of the onshore export cable where practical. | Co78 has been updated to make it clearer. No information has been changed.
Co79 | Scoping | Severance to PRoW will be temporary where possible, and appropriate temporary diversions, gated crossings and signage will be provided and/or temporary PRoWs/footpath diversions will be provided during construction. PRoW will be reinstated as soon as reasonably practical. Where permanent severance to PRoW is necessary, permanent diversions of such routes will be applied. | Co79 has been updated with the latest PEIR information regarding PRoW crossings.
Co80 | Scoping | A crossing schedule is provided which includes crossing methodology for each crossing of road, rail, PRoW and watercourse. | The crossing schedule is now referred to in Co7, Co27 and Co34, so Co80 has therefore been removed, to streamline the commitments presented.
Co81 | Scoping | A scour protection layer (typically rock) may be needed where cable burial depths cannot be obtained. Where scour protection is required, MGN 543 (or latest relevant available guidance) will be adhered to with respect to changes greater than 5% to the under keel clearance. | Co81 has been updated with updated PEIR information regarding scour protection.
Co82 | Scoping | A scour protection layer (typically rock) may be needed on the seabed and would be installed either before or after foundation installation. A Scour Protection Management Plan will be developed. It will include details of the need, type, quantity and installation methods for scour protection. | The detail regarding scour protection has been removed here, as the commitment now references the Scour Protection Management Plan, which will contain this information.
Co83 | Scoping | Undertake a cable burial risk assessment to inform front end engineering works. Where possible, cable burial will be the preferred option for cable protection. | Co83 has been changed to make a specific commitment in relation to cable burial as the preferred option for cable protection. Co176 povides a commitment to develop a Cable Specification and Installation Plan. An appropriate dML Condition is included witin the Draft DCO.
Co84 | RPSS | Foundations and cable routes Presence of sensitive habitats will be identified through a review of the latest available benthic datasets and pre-construction surveys. Wind turbine foundations and the offshore export cable will be micro-sited around annex one habitat wherever reasonably practicable qualifying sensitive habitat features (subject to agreement with the MMO) to an extent not resulting in a hazard for marine traffic and Search & Rescue capability. Presence of sensitive habitats will be identified through a review of the latest available benthic datasets and pre-construction surveys. | Co84 has been updated to include reference to micro-siting around Annex 1 habitat.
Co86 | RPSS | The proposed offshore export cable corridor and cable landfall (below MHWS) will not cross the Greater Wash SPA, Flamborough & Filey Coast SPA and the Flamborough Head SAC. all statutory marine designated areas. | Co86 has been updated to include specific reference to the relevant designated sites.
Co88 | Scoping | Construction and operational maintenance vessels (e.g. CTVs) will follow a route from their home port that avoid high concentrations of rafting red-throated diver. (a species known to be sensitive to disturbance by boat traffic). | The commitment has been updated to ensure it is clear, appropriate and practicable whilst ensuring disturbance to red-throated diver from vessel traffic is minimised.
Co89 | Scoping | Advance warning and accurate location details of construction, maintenance and decommissioning operations, associated Safety Zones and advisory passing safety distances will be given to fishing fleets (including via Notices to Mariners and Kingfisher Bulletins). | Co89 has been updated to make it clearer to read.
Co90 | Scoping | Ongoing liaison with fishing fleets will be maintained during construction, maintenance and decommissioning operations via an appointed Fisheries Liaison Officer and Fishing Industry Representative. | This commitment has been updated to make it clearer. No information has been changed.
Co91 | Scoping | Guard vessels will be used, where appropriate, during construction/maintenance/decommissioning operations to ensure communication of and adherence to Safety Zones and advisory safety distances. | At the point of scoping, two commitments were proposed (Co91 &Co139), in relation to the use of safety zones and guard vessels during construction/maintenance/decommissioning. A single commitment is now proposed and all details are included in Co139.
Co92 | RPSS | All infrastructure (including partially constructed/decommissioned) will be designed, marked and lit in accordance with standard industry guidance including MGN 543, CAP 764, CAP 437 and as advised by IALA and Trinity House. | Co92 had details relevant to MGN 543 guidance, specifying that infrastructure will be designed, marked and lit in accordance with this guiance. This has been removed, as a commitment to comply with MGN 543 is included in Co99.
Co93 | RPSS | Aids to navigation (marking and lighting) will be deployed in accordance with the latest relevant available standard industry guidance and as advised by Trinity House, MCA and Civil Aviation Authority (CAA) and MoD as appropriate. This will include a buoyed construction area around the array area and the HVAC booster station in consultation with Trinity House. | Co93 has been updated to include reference to the relevant bodies who Hornsea Four will consult with on aids to navigation, and further information regarding the types of aids to navigation.
Co94 | RPSS | The United Kingdom Hydrographic Office will be notified Notificaitons will be made to the relevant bodies (e.g. United Kingdom Hydrographic Office) of both the commencement (within two weeks), progress and completion of offshore construction works (within two weeks) to allow marking of all installed infrastructure on nautical charts. | Co94 has been updated to ensure alignment with the details included in the draft DCO.
Co95 | Scoping | A fisheries co-existence and liaison plan will be prepared prior to the conmencement of construction in advance of construction commencing. | Co95 has been updated to mae it clearer to read. The draft dMLs of the draft DCO includes a Condition to prepare a Fisheries Liaison and Coexistence Plan.
Co96 | Scoping | Maintaining at least one line of symmetry/orientation in turbine layout The project commits to agreeing layout principles with MCA, which will include maintaining at least one line of symmetry/orientation in turbine layout. | Co96 has been updated to reflect the production of th Laout Principles and to include the MCA as a onsultee on the development of these principles.
Co98 | Scoping | Construction Monitoring of vessel traffic for the duration of the construction period and coordination for project vessels. | Co98 has been updated to make it clearer to read.
Co99 | Scoping | Development of Emergency Response and Cooperation Plan (ERCOP) Hornsea Four will ensure compliance with MGN543 where appropriate. | Co99 has been updated to ensure alignment with the details included in the draft dMLs of the DCO.
Co101 | Scoping | Air draught clearance of blades greater than 22m above MHWS. 23,8m MSL | Co101 has been replaced by Co138 which provides a commitment in relation to air draught clearance.
Co102 | Scoping | Notification to aviation stakeholders of the location and height of all wind energy development and associated construction activities (all structures over 150 ft). The Defence Geographic Organisation will be informed of the locations, heights and lighting status of the wind turbines, including estimated and actual dates of construction and the maximum height of any construction equipment to be used, prior to the start of construction, to allow inclusion on Aviation Charts. | Co102 has been updated to ensure alignment with the details included in the draft dMLs of the DCO.
Co105 | Scoping | All structures (turbines and offshore support platforms) above 60 m in height to be fitted with aviation obstruction lighting. | Co93 will ensure that marking and lighting is deployed in line with industry guidance. Therefore, Co105 has been removed to streamline the Commitments presented.
Co106 | Scoping | Turbines to be accessed by hoist will be equiped with a helihoist status light on each turbine to indicate to a helicopter operator that the turbine blades and nacelle are safely secured in position prior to helicopter hoist operations commencing. | Co99 will ensure that helihoist status light will be provided where necessary. This information will be detailed in MGN543.
Co107 | Scoping | Crossing and proximity agreements with known existing pipeline and cables operators will be sought. | Co107 has been updated to make it clearer.
Co108 | Scoping | A vessel management plan will be developed pre construction which will determine vessel routing to and from construction areas and ports to minimise encounters with marine mammals. avoid areas of high risk. This will also include codes of conduct for vessel behaviour and for vessel operators including advice to operators to not deliberately approach marine mammals and to avoid abrupt changes in course or speed should marine mammals approach the vessel to bow-ride. | Co108 has been update to clarify the timing in relation to the development of the vessel management plan.
Co109 | Scoping | During piling operations, soft starts will be used, with lower hammer energies used at the beginning of the piling sequence before increasing energies to the higher levels. | Co109 had details relevant to piling and hammer energies. Measures relating to piling are now contained within Co110 which notes that a MMMP will be implemented during construction, and includes the infomration from Co109.
Co110 | Scoping | A piling Marine Mammal Mitigation Protocol (MMMP), approved by the MMO in consultation with Natural England, will be implemented during construction and will be developed in accordance with JNCC (2010) guidance. The piling MMMP will include details of soft starts to be used during piling operations with lower hammer energies used at the beginning of the piling sequence before increasing energies to the higher levels. The MMMP will outline monitoring measures to ensure the impact zone is free of marine mammals before piling commences. The details of the MMMP will be agreed with Natural England. | Co110 has been updated to include reference to the JNCC (2010) guidance. An Outlline MMMP has been produced which includes further details on appropriate measures to be implemented (see document F2.5)
Co111 | Scoping | A PEMMP (construction and operation phases) and Decommissioning Plan (decommissioning phase) will be produced and followed. The PEMMP and Decommissioning Plan will cover the construction, operation and maintenance, and decommissioning phases of Hornsea Four respectively and will include A Marine Pollution Contingency Plan (MPCP) will be developed. This MPCP will outline procedures to protect personnel working, safeguard the marine environment and mitigation measures in the event of an accidental pollution event arising from offshore operations relating to Hornsea Four. The MPCP will also outline mitigation measures should an accidental spill occur, address potential contaminant releases and include relevant key emergency contact details (e.g. Environment Agency, Natural England and MCA). | Details relating to decomissioning have been removed from this commitment as the production of a Decomissioning Strategy is covered under Co181. The wording of this commitment relevant to a MPCP has been updated to ensure consistency with the wording in the draft dMLs of the DCO.
Co112 | Scoping | A UXO specific (MMMP), approved by the MMO in consultation with Natural England will be implemented during UXO clearance. The UXO MMMP will use ADDs, marine mammal observers and scare charges as the primary mitigation measures alongside other measures as may be agreed with Natural England and the MMO. | Removed this as Hornsea Four are not consenting the removal of UXO under the DCO. If UXO detonation is required, Hornsea Four will seek the relevant Marine Licence approvals which will be subject to their own conditions as required.
Co113 | Scoping | A Decommissioning Marine Mammal Mitigation Protocol (MMMP), approved by the MMO in consultation with Natural England, will be implemented during decommissioning. The Decommissioning MMMP will include robust measures to ensure the risk of permanent threshold shift (PTS) to marine mammals is negligible and will be in line with the latest relevant available guidance. outline monitoring measures to ensure the impact zone is free of marine mammals before decommissioning activities commences. The details of the MMMP will be agreed with Natural England. | Co113 has been updated to make it clearer and to note that the latest relevant available guidance will be followed.
Co114 | Scoping | Best practice air quality management measures will be applied where it is relevant, as described in Institute of Air Quality Management (IAQM) Guidance on the Assessment of Dust from Demolition and Construction 2014, version 1.1, or latest relevant available guidance, where relevant and practicable to the activities being undertaken. | Co114 has been updated to make it clearer and to note the use of the latest available guidance. | Pre-commencement of licensed activities | MMO | n/a
Co116 | Scoping | Any contamination encountered during the construction phase would be subject to appropriate risk assessment and if necessary, either removed, treated and/ or mitigated as part of the project. | Co116 had details relevant to contamination risk assessment. This has been combined with Co77, which notes that a contaminated land and groundwater scheme will be prepared, which will identify any contamination and measures. The preparation of a contamination scheme is also included as a requirement in the draft DCO.
Co123 | Scoping | Based on noise modelling results, where noise has the potential to cause significant adverse effects, the use of mufflers and acoustic barriers will be used where HDD is being undertaken. and directional lighting for areas where HDD is undertaken. | Details in relation to directional lighting have been removed from this commitment as they are covered in Co69
Co124 | Scoping | Adoption of an agreed Implementation of A Construction Code of Construction Practice (CoCP) will be developed in accordance with the outline CoCP. The outline CoCP will include measures to minimise reduce temporary disturbance to residential properties, recreational users and existing land users. | Co124 has been updated to reflect that an Outline CoCP has been provided. The development of a CoCP is included as a requirement within the draft DCO.
Co127 | Scoping | An Onshore Decommissioning Plan or method statement will be agreed developed prior to decommissioning. The Onshore Decommissioning Plan will include provisions for with the removal of all onshore above ground infrastructure and the decommissioning of below ground infrastructure and details relevant to pollution prevention and avoidance of ground disturbance. The Onshore Decommissioning Plan will be in line with the latest relevant available guidance. | Co127 has been updated with the latest PEIR information, which now has further information regarding what the Onshore Decommissioning Plan will include. The development of an onshore Decommissioning Plan is included as a requirement within the draft DCO.
Co128 | Scoping | Appropriate sites will be selected through the RPSS process for onshore logistics compounds. Good construction practice will be applied. | Co128 is is no longer necessary as this has already been undertaken through the site selction process. Co128 is therefore removed, to streamline the commitments presented.
Co133 | RPSS | The onshore export cable corridor (ECC) will be routed to avoid residential receptors noise sensitive properties avoided by at least 50 m. | Co133 has been updated to make it align with the PEIR glossary. No information has been changed.
Co134 | RPSS | Cable installation works at the landfall area will be located at least 200 m from residential receptors noise sensitive properties. | Co134 has been updated to make it align with the PEIR glossary. No information has been changed.
Co135 | RPSS | Temporary construction highway access points access roads along the onshore export cable corridor (ECC) will be located at least 150m from residential receptors, with the exception of two receptors: Bridge Farm Holiday Cottages, Brigham, Driffield, and a receptor off the A1035 Malton Road, Beverley. noise sensitive properties. | Co135 has been updated with the latest PEIR information and to include details of exceptions where temporary highway access points may need to be closer than the specified minimum distance.
Co137 | Scoping | HGV vechicle movements associated with operation and planned maintenance of the onshore infrastructure will operate only between the hours of during the daytime and evening periods (i.e. 0700 – 2300. HGV vehicle movements may however be subject to unscheduled maintenance activities events outside these hours. In this event the council will be informed via writing. | Co137 has changed reference of vehicle movements to HGV movements which is in line with the latest PEIR information.
Co138 | Scoping | Raised Lower air draught of WTG wind turbines to will be a minimum of 35 m above Mean Sea Level (MSL) instead of 22 m LAT | Co138 has been updated to make it clearer to read. No information has been changed.
Co139 | Scoping | Application and use of Safety zones of up to 500m will be applied during construction, maintenance and decommissioning phases. Where appropriate, guard vessels will also be used to ensure adherence of Safety Zones or advisory passing distances , as defined by risk assessment, to mitigate any impact which poses a risk to surface navigation during construction, maintenance and decommissioning phases. Such impacts may include partially installed structures or cables, extinguished navigation lights or other unmarked hazards. | Co139 has been updated to make it clearer to read. Information regarding the use of guard vessels has been added.
Co140 | RPSS | Establishment of archaeological exclusion zones (AEZs) as required to protect any known / identified marine archaeological receptors. Archaeological exclusion zones (AEZs) will be established in the Marine WSI in accordance with the outline Marine WSI (document reference F2.4), to protect any known / identified marine archaeological receptors. | Co140 has been reworded to note that full details of archaeological exclusion zone which are known at this stage are provided within the Outline Marine WSI (see document F2.4)..
Co141 | Scoping | A Marine Written Scheme of Archaeological Investigation (WSI) will be developed in accordance with the Outline Marine WSI. Development and agreement of an archaeological WSI. The Marine WSI will includeing the development and implementation of a protocol for Archaeological Discoveries in accordance with ‘Protocol for Archaeological Discoveries: Offshore Renewables Projects’ (The Crown Estate, 2014). | Co141 has been updated to make it clearer to read. It is noted an Outline Marine WSI is provided (see document F2.4).
Co142 | Scoping | A programme of geoarchaeological assessment and analysis will be undertaken on geotechnical samples collected across the ECC and array area, which will include early engagement with the geoarchaeologist to optimise sample locations, and will result in the delivery of a paleogeographic ground-model. | Co142 details relevant to geoarchaeology assessment. This has been combined with Co141, which states that a Marine Written Scheme of Archaeological Investigation (WSI) will be developed in accordance with the Outline Marine WSI.This WSI will cover all of the information that was named in Co142. In addition Co166 and Co167 provided commitments for geophysical and geotechnical surveys including a full archaeological review.
|  |  |  | n/a | n/a | n/a
Co139

## 6.Public Commitments
6. Public Commitments
Public Commitment Reference | Public Commitment/Comment | Hornsea Four Action | Relevant Commitment Reference | Hornsea Four Response
PCo1 | Be aware and avoid iron age fortification near Gembling and British roman settlements around Beck Hill | Amended Commitment | Co2 | Co2 has been amended to include avoidance of heritage assets.
PCo2 | Full consultation with parish and county council - Foston on the Wolds PC and ERYC | Noted | n/a | Whilst this request is not a commitment as such, the Hornsea Four have already begun engagement with parish and county councils na dwill continue to engage throught the development of Hornsea Four. This is in the form of face to face meetings as well as inviting ERYC to take part in our Evidence Plan process.
PCo3 | Agree levels of noise, vibration and lighting levels with ERYC - especially with HDD works, if undertaken at night and close to housing | Refer to existing commitment | Co124; Co123; Co133; Co134; Co135 | Under Co124, a Code of Construction Practice will be prepared with measures referring to noise, vibration and lighting. In addition, "Core working hours for the construction of the onshore components of Hornsea Four will be as follows: • Monday to Friday: 07:00 - 18:00 hours; • Saturday: 07:00 - 13:00 hours; • Up to one hour before and after core working hours for mobilisation (“mobilisation period”), i.e. 06:00 to 19:00 weekdays and 06:00 to 14:00 Saturdays; and • Maintenance period 13:00 to 17:00 Saturdays. Activities carried out during mobilisation and maintenance will not generate significant noise levels (such as piling, or other such noisy activities). Full details of working hours are provided within the Code of Construction Practice. In addition the following commitments: Co123, Co133, Co134, Co135 refer to further measures in relation to noise and lighting.
PCo4 | There should be no/minimal increase in traffic movements within the village - There should be commitments for exact figures | New commitment | Co144 | Co144: A construction Traffic Mangement Plan (TMP) will be developed in accordance with the outline construction TMP. The construction TMP will include; 1. details of times and vehicle movement numbers and measures to ensure minimal to no increase in traffic movements through Barmston village; and 2. targeted road safety measures for example, providing new and appropriate road signage for temporary road alterations.
PCo5 | Commit to specific substation locations | Noted | n/a | The DCO application will seek approval for only one Onshore Substation (OnSS) location in proximity to the NGET substation at Creyke Beck. The location of the OnSS is the onshore Works Plans (D1.4.2)
PCo6 | Minimum construction and completed promptly | Noted | n/a | The maxium duration of the onshore works is expected to last 36 months for the Onshore Substation, 36 months for the onshore Export Cable Corridor Logistics Compounds and 30 months for the onshore export cable.
PCo7 | Consider moving scoping boundary further west to exclude Leconfield. | Noted | n/a | The 80 m cable corridor has been routed to avoid all residential properties, priority habitats and ancient woodlands, and is currently located to the east of Cherry Burton and to the west of Leconfield.
PCo8 | Minimise noise, vibration and traffic disruption to Leconfield and surrounding villages - e.g. Working hours commence after 8am and finish 5pm, no Sunday working and reduced weekend working | Refer to existing commitment | Co124; Co123; Co133; Co134; Co135 | Under Co124, a Code of Construction Practice will be prepared with measures referring to noise, vibration and lighting. In addition, "Core working hours for the construction of the onshore components of Hornsea Four will be as follows: • Monday to Friday: 07:00 - 18:00 hours; • Saturday: 07:00 - 13:00 hours; • Up to one hour before and after core working hours for mobilisation (“mobilisation period”), i.e. 06:00 to 19:00 weekdays and 06:00 to 14:00 Saturdays; and • Maintenance period 13:00 to 17:00 Saturdays. Activities carried out during mobilisation and maintenance will not generate significant noise levels (such as piling, or other such noisy activities). Full details of working hours are provided within the Code of Construction Practice. In addition the following commitments: Co123, Co133, Co134, Co135 refer to further measures in relation to noise and lighting.
PCo9 | Siting of the onshore substation as close to Creyke Beck as possible | Noted |  | The DCO application will seek approval for only one Onshore Substation (OnSS) location in proximity to the NGET substation at Creyke Beck. The location of the OnSS is the onshore Works Plans (D1.4.2)
PCo10 | Minimise visual intrusion, especially the view of Beverley Minster from the A1079 | New commitment | Co145 | Refer to Co. 145: Views of Beverley Minster from the A1079 will not be obstructed by the siting of the onshore substation,
PCo11 | Minimise disruption to PROWs | New commitment | Co79; Co165 | Co. 79: Severance to PRoW will be temporary where possible, and appropriate temporary diversions and signage will be provided during construction. PRoW will be reinstated as soon as reasonably practicle. Where permanent severance to PRoW is necessary, permanent diversions of such routes will be applied. New commitment - Co. 165: Where PRoWs are required to be closed during the construction of the onshore connection works, they will not be closed for any longer than three months at any one time, or for five months in total over the whole construction period. Where closures are required for longer period, East Riding of Yorkshire Council will be informed in writing.
PCo12 | Full restoration of landscape | Refer to existing commitment | Co10; Co28; Co30; Co162 | Hornsea Four have commited to developing a Landscape Plan which will provide detail on planting measures: Co10: A Landscape Management Plan will be developed in accordance with the outline Landscape Management Plan. The plan will include details of mitigation planting at the onshore substation site, including number, location and species. Details of management and maintenance of planting will be provided. Where practical, landscape mitigation planting will be established as early as possible in the construction phase. Hornsea Four have made a number of other Commitments which are relevant to restoration of the lnadscape: Co28; Co30; Co162
PCo13 | Non-interference with all drainage systems - consider offering assistance to internal drainage board i.e. flood assistance | New commitment |  | We can not commit to non-interference with all drainage systems. However, we can propose to commit to offering assistance to the internal drainage board. Co. 147: Appropriate liaison will take place with the Internal Drainage Board during construction.
PCo14 | Take account of cliff erosion at landfall - 2cm per year on average, with Fraisthorpe-Bridlington beach a recreation hotspot | Noted | n/a | Erosion at the landfall is considered within the Flood Risk Assessment (A6.2.2) and the Marine Processes Technical Report (A5.1.1)
PCo15 | Commitment to making to taking the project forward and making it work | Noted | n/a | Orsted are committed to delivering this project and plan to submit our DCO application in 2019.
PCo16 | Do not use Foston on the Wolds for traffic/vehicles | Noted |  | Please refer to Co171 - HGVs will avoid travel through Foston on the Wolds
PCo17 | Ensure that the onshore substation is screened by trees to limit the visual impact. | New commitment | Co30 | The following new commitment has been added: Co. 30: A Landscape Mangement Plan will be developed in accordance with the outline Landscape Management Plan. The plan will include details of mitigation planting at the onshore substaton site, including number, location and species. Details of management and maintenance of planting will be provided. Where practice, landscape mitigation planting will be established as early as possible in the construction phase.
PCo18 | Ensure that the English Coastal Path is adequately provided for, with the planned activity and that all existing footpaths/access roads are maintained - E.G. Minster Way | New commitment | Co158 | The following new commitment has been added: Co. 158: Impacts on the English Coast Path national route will be minimised by avoiding impacts through site design and phasing within working constraints for the landfall construction. In addition, Co79 will be applied to the English Coast Path national route.
PCo19 | Ensure no long term impact and disruption to productive land for the next few years and long term drainage of fields if needed. | Noted | Co19 | Noted. Volume 3, Chapter 4 (Land Use and Agriculture) provides an assessment of effects from the construction of Hornsea Four. Further, the following new commitment has been added: Co. 19: An Onshore Infrastructure Drainage Strategy will be developed for the permanent operational development along the onshore cable corridor and the onshore substation, and will include measures to ensure that existing land drainage is reinstated and maintained, and measures to limit discharge rates and attenuate flows such that pre-development run-off rates to surrounding land are retained. The Onshore Infrastructure Drainage Strategy will be developed in consultation with the Lead Local Flood Authority, Environment Agency, Lead Local Flood Authority and relevant Internal Drainage Board as appropriate.
PCo20 | No construction traffic (for onshore substation) via Cottingham and Dunswell | New commitment | Co150 | The following new commitment has been added: Co. 150: A new access will be taken directly from the A1079, to route construction traffic away from Cottingham and Dunswell,
PCo21 | All traffic via dedicated access from A1079. On completion this access to be used for emergence only. | Noted | Co150 | Please refer to Co150. Temporary construction access will come from the northbound carriageway of the A1079. Permanent operation and maintenance access are currently expected to be taken from the south using Park Lane Road. The road will be removed upon completion of the construction phase.
PCo22 | No buildings to obstruct view from St Mary's Church Cottingham and Beverley Minister | New commitment | Co151 | The following new commitment has been added: Co. 151 - No above ground infrastructure associated with Hownsea Four will obstruct the view from St Mary's Church Cottingham to Beverley Minister through considered design of the OnSS and site selection
PCo23 | Drainage concerns about particular fields, with land only re-drained 5 years ago. Problems previously with water pipe and electricity cable with drainage after work has been completed. | New commitment | Co19 | The following new commitment has been added: Co. 19: An Onshore Infrastructure Drainage Strategy will be developed for the permanent operational development along the onshore cable corridor and the onshore substation, and will include measures to ensure that existing land drainage is reinstated and maintained, and measures to limit discharge rates and attenuate flows such that pre-development run-off rates to surrounding land are retained. The Onshore Infrastructure Drainage Strategy will be developed in consultation with the Lead Local Flood Authority, Environment Agency, Lead Local Flood Authority and relevant Internal Drainage Board as appropriate.
PCo24 | Do not deviate from plans for underground cables with no booster stations | Noted | n/a | The work put into planning the underground cables takes many years, therefore it is highly unlikely that deviation will be necessary. In the event that any changes to plans will be agreed with landowners.
PCo25 | Viable plan or commitment to remove all offshore sea bed infrastructure at end of life of this project | New commitment | Co181 | A Commitment to produce an offshore Decomissioning Plan has been added to the Commitment Register, see Co181.
PCo26 | Be open and transparent at all times, keeping the public informed | Noted | n/a | Hornsea Four have already begun engagement with parish and county councils as well as key stakeholders and members of the public. This is in the form of face to face meetings, public information events as well as specialist working groups to discuss key topics.
PCo27 | Commit to plans w.r.t. flood risk. Land to rear of property as flooded in the past and water table is exceptionally high | New commitment | Co14 | The following new commitment has been added: Co. 14: An Onshore Infrastructure Drainage Strategy will be developed for the temporary construction works, to ensure that existing land drainage is maintained during construction. Specific drainage measures for each area of land will be specified based on information identified and recorded by a Land Drainage Consultant prior to construction. The Onshore Infrastructure Drainage Strategy will be developed in consultation with landowners, the Lead Local Flood Authority, Environment Agency and relevant Internal Drainage Board.
PCo28 | Be aware of local chalk rivers and avoid, which are under threat from urban development (see E. Yorkshire Rivers Trust Website) | Amend existing commitment | Co1 | Co. 1 - All main rivers, IDB maintained drains, main roads and railways will be crossed by HDD or other trenchless technology as set out in the onshore crossing schedule. Where HDD technologies are not practical, the crossing of ordinary watercourses may be undertaken by open cut methods. In such cases, temporary measures will be employed to maintain flow of water along the watercourse.
PCo29 | Honour commitments made by land agent with respect to farms within Scoping Boundary | Noted | n/a | Engagement with land owners and land agents will be ongoing as the Scoping Boundary is further refined.
PCo30 | No overhead pylons | Amended Commitment | Co25 | Co25: The onshore export cable corridor will be completely buried underground for its entire length. No overhead pylons will be installed as part of the consented works for Hornsea Four.
PCo31 | No digging up or damage to roads in the village of Foston on the Wolds | Amend existing commitment | Co1 | Co. 1 - All main rivers, IDB maintained drains, main roads and railways will be crossed by HDD or other trenchless technology as set out in the onshore crossing schedule. Where HDD technologies are not practical, the crossing of ordinary watercourses may be undertaken by open cut methods. In such cases, temporary measures will be employed to maintain flow of water along the watercourse.
PCo32 | We want the onshore scoping boundary to stay the same i.e. not any closer to our property | Noted | n/a | The boundaries will not extend further than the PEIR boundnary which has been develoepd.
PCo33 | Consider EMFs and the efficacy of cable shielding, reducing the distance the EMF travels underground | Refer to existing commitment | Co83 | Co83: Where possible, cable burial will be the preferred option for cable protection.
PCo34 | Consider cliff erosion at landfall and the impact of climate change | Noted | n/a | Impacts are considered in Onshore infrastructure Flood Risk Assessment (Volume 6, Annex 6.2), and Marine Geology, Oceanography and Physical Processes (Volume 2, Chapter 1). Details of installation methodology at the landfall are presented within the Project Description (Volume 1, Chapter 4).
PCo35 | Take as small acreage as possible for the buildings required | Noted | n/a | Noted, Orsted will aim to take the minimm land required which ensures the feasibility of the project.
PCo36 | Commit to landscaping and screening to lessen the visual impact | New commitment | Co10;Co30 | Co10 states: "Post-construction the working area will be reinstated to pre-existing condition as far as reasonably practical in line with DEFRA 2009 Construction Code of Practice for the Sustainable Use of Soils on Construction Sites PB13298." The following new commitment has been added: Co. 30: A Landscape Mangement Plan will be developed in accordance with the outline Landscape Management Plan. The plan will include details of mitigation planting at the onshore substaton site, including number, location and species. Details of management and maintenance of planting will be provided. Where practice, landscape mitigation planting will be established as early as possible in the construction phase.
PCo37 | Field drainage - I would like long term commitments to possible long term drainage problems - it is not possible to repair field drains properly in one year due to land settlement | New commitment | Co14 | Co. 14: A The following new commitment has been added: Co. 14: A Construction Drainage Scheme will be developed for the temporary construction works, to ensure that existing land drainage is maintained during construction. Specific drainage measures for each area of land will be specified based on information identified and recorded by a Land Drainage Consultant prior to construction. The Construction Drainage Scheme will be developed in consultation with landowners, the Lead Local Flood Authority, Environment Agency and relevant Internal Drainage Board. Co19. An Onshore Infrastructure Drainage Strategy will be developed for the permanent operational development along the onshore cable corridor and the onshore substation, and will include measures to ensure that existing land drainage is reinstated and maintained, and measures to limit discharge rates and attenuate flows such that pre-development run-off rates to surrounding land are retained. The Onshore Infrastructure Drainage Strategy will be developed in consultation with the Environment Agency, Lead Local Flood Authority and relevant Internal Drainage Board as appropriate.
PCo38 | Consider access carefully, with single access to Brigham through the village lane and over a small bridge. | Noted | n/a | A traffic assessment has been undertaken and is presented in Traffic and Transport chapter (Volume 3, Chapter 7). Appropriate traffic management measrues will be detailed and agreed through the Outline Construction Traffic and Travel Plan (F2.2).
PCo39 | Landfall area just skims farm land to the north of our house. Please commit to the cables avoiding this land, as it involves crossing ditches, two strips of woodland and wildlife area. | Noted | n/a | A refined PEIR boundary has been developed. This will not be extended beyond the planned boundary.
PCo40 | To consider local wildlife and habitats, especially marine life | Noted | See Commitment Register | Hornsea Four have set out to adopt Commitments to reduce impacts on local wildlife within the onshore and offshore environmnets wherever possible. A number of commitments are therefore relevant; these include but are not limited to Co2; Co26; Co27; Co30; Co33; Co44; Co45; Co48; Co78; Co84; Co86; Co87; Co88; Co110; Co111; Co113; Co119; Co120; Co168
PCo41 | Minimum impact on Barmston Village | New commitment | Co144 | The following new commitment has been added: Co144: A Construction Traffic Management Plan (CTMP) will be developed in accordance with the outline CTMP to be submitted with the DCO application. The CTMP will set standards and procedures for: 1. Managing the numbers and routeing of HGVs during the construction phase; 2. Managing the movement of employee traffic during the construction phase; 3. Details of localised road improvements necessary to facilitate safe use of the existing road network; and 4. Details of measures to manage the safe passage of HGV traffic via the local highway network
PCo42 | Avoid works around Barmston drain to avoid village flooding | New commitment | Co143 | The following new commitment has been added: Co. 143: The landfall site that will avoid the Barmston Main Drain.
PCo43 | Take consideration into protected wildlife on our land; including Bats, Great Crested Newts, Badgers, Egrets, Barn Owls and other wildlife. | Refer to existing commitment | n/a | Hornsea Four have set out to adopt Commitments to reduce impacts on local wildlife within the onshore and offshore environmnets wherever possible. A number of commitments are therefore relevant; these include but are not limited to; Co33; Co87; Co119; Co120; Co168;
PCo44 | Under the 'grey' area (temporary works) you need to protect hedgerows and mature trees surrounding properties and confirm your intentions i.e. open cut trench method - confirm that you will moved the trench into open land as removal/disturbance will have an unnecessary irreversible impact | Amended Commitment | Co26; Co78 | Co. 26: Hedgerows and vegetation will be retained where possible. Where it is not possible to retain them, hedgerows will be removed prior to topsoil removal. The width of hedge and vegetation removed will be limited where practical. Removed hedges, trees will be replaced with locally appropriate native species. Co. 78: Trees identified to be retained as per the Onshore Crossing Schedule will be fenced off and worked around. Where works close to trees that will remain in situ are required, techniques will be used to safeguard the root protection zone
PCo45 | There should be no works for the trench near our land (passes Foston on the Wolds and turns to the bottom of Gembling Village). This area has mature trees and hedgerows, including English Oaks, with preservation orders being sought. You can move the trench to the south of Gembling meaning work in open field. | Refer to existing commitment | Co2; Co27 | Please refer to Co2 and Co27.
PCo46 | Avoidance of Brigham Quarry, which has remaining reserves of approximately 750,000 tonnes of gravel/limestone/chalk. These will be vital supplies in the future of over the next 5 years. The quarry is also under planning permission as a caravan site.- the proposed cable route area bisects the caravan park area. | Noted | n/a | The Onshore ECC avoids Brigham Quarry.
PCo47 | Make clear commitments to visibility of the offshore area from the Yorkshire coast - including visibility of blade tips | Noted | n/a | Please refer to the Seascape, Landscape Visual Resources Assessment (Volume 2, Chapter 11). Where an assessment of project visibility of the offshore coast is provided.
[5 empty] | Pre-commencement of licensed activities | MMO | n/a
[5 empty] | n/a | n/a | n/a
Co139